## Sheet1
Road and Traffic Schemes January 2026
Traffic Scheme List Last Updated 20/1/2025
Location | Town | Description | Status
B5151 High Street | Dyserth | Second phase of scheme to relieve congestion. Details are still being decided. | Under consideration
Clos David Owen, Hylas Lane, Abbey Road, Castle Street | Rhuddlan | Waiting restrictions | Under consultation
Llanfair Road, Wrexham Road | Ruthin | Waiting restrictions | Under consultation
East Parade | Rhyl | Coach Parking bays & Loading Bays | Under consultation
B5437 Carrog | Carrog, Corwen | Waiting restrictions | Under consultation
Allt Yr Efail (Village Road) Ffynnon Tegla junction | Llandegla | No loading restrictions | Under consultation
Westbourne Avenue/Seabank Road | Rhyl | Waiting restrictions | Under consultation
Various Steets in Prestatyn East Ward | Prestatyn | Waiting restrictions | Under consultation
Various Steets in Rhuddlan | Rhuddlan | Waiting restrictions? | Under consultation
A525/A543 Townsend Junction | Denbigh | Traffic Signal Refurbishment, surface in poor condition | Under development
High Street nr Parliament Street | Rhuddlan | Puffin Crossing Refurbishment | Under development
High Street nr Vicarage Lane | Rhuddlan | Puffin Crossing Refurbishment | Under development
Market Street | Llangollen | Possible traffic management scheme to improve compliance with existing one way restriction | Under development
Castle Street/Mill st/Abbey Rd | Llangollen | Keep Clear Marking
St Peter's Square, Market Street, Well Street | Ruthin | Changes to kerblines, public realm improvements, changes to parking restrictions | Under development
High Street, Sussex Street, Market Street, Glanglasfor | Rhyl | Repaving of existing pedestrianised areas, various other public realm improvements | Under development
Vicarage Road | Llangollen | Carriageway construction, road widening and drainage works | Maintenance
Aberkinsey, Dyserth Road | Rhyl | New housing development. Phase 4 and 5 underway | Construction
Henllan Street | Denbigh | New residential development. Highway works complete. Contractor went into liquidation | In Progress
Ruthin Road | Denbigh | Improvements and surfacing to right turn lane. Awaiting confirmation of road space availability | In Progress
Bryn Gobaith - St Asaph | St Asaph | New housing development surfacing works | On site
B5429 | Llandyrnog | New housing development including formation of a new access | Nearing completion
Ffordd Cae Felin | Prestatyn | New housing development. Access extension from Cae Felin | On going
Upper Denbigh Road | St Asaph | New housing development. New right turn access into site and footways on both sides of the A525. | Construction
Bryn Morfydd Access Road Opposite Llewysog Isaf | Llanrhaeadr | New lodge develpoment. Section 278/38 works involve passing places and new accesses into site. Minimal involement to date | On going
A525 | Llanrhaeadr | New housing development including new access onto A525. Re-location of 20mph speed zone | On going
Gwaenynog Road | Denbigh | New housing development incuding formation of new access | On going
Gronant Road | Prestatyn | Housing development (9 plots) | Maintenance
Rhuddlan Road (Opposite Hospital) | Bodelwyddan | Housing development (108 dwellings). Section 278 works including installation of Toucan Crossing on Rhuddlan Road | Construction
Edward Henry Street | Rhyl | Demolition of exisiting flats and housing development. Section 278 works to footways and re-surfacing works | Maintenance
Bryn Golau | Saron | Minor carrigeway widening and new access to chicken farm. Section 278 agreement | Waiting for start date
Ysgol Pendref | Denbigh | New housing development including access | Construction
Midnant Farm | Prestatyn | New housing development including access | Construction
Awel y Mor offshore windfarm | St Asaph | Construction access arrangement from B5381 Glascoed Road | Consultation
Warren Drive | Prestatyn | Section 278 works to footway and traffic calming | Waiting for start date
Ffordd Yr Onnen, Lon Parcwr Business Park | Ruthin | Subdivision of existing unit into 3 units and construction of a new vehicular. Section 278 agreement | Waiting for start date
Pany Y Maen Wind Farm | Clocaenog | Minor works requried for access to windfarm. Section 278 agreement | Waiting for start date
Alexander Drive (Plas Newydd) | Prestatyn | Estate road, new access, utility connections | Construction
Cynwyd to A5 west of Corwen (including new crossing near junction with B4401) | Corwen | New active travel route | Under development
East and West Parade | Rhyl | Major redesign of highway, active travel routes, crossing points | Under development
Ffordd Pendyffryn/Bridge Road/Gas Works Lane Junction | Prestatyn | Active Travel route/facilities | Under development
Nant Hall Road, Prestatyn | Prestatyn | Active Travel route/facilities | Under development
Grove Road to Home Bargains Retail Park | Denbigh | Active Travel route | Under development
Lenten Pool | Denbigh | Improvements to roundabout to improve active travel provision and road safety | Under development
H-Bridge | Rhyl | Provision of active travel route/facilities over bridge | Under development
Llanrhydd Street | Ruthin | Improvement to existing stepped access | Detailed design stage
Brook Street, Maes Pengwern | Llangollen | Active Travel route | Under development
Station Network Plan | Rhyl | AT routes to railway and bus station
Hylas Lane/Castle Street, Rhuddlan | Rhuddlan | AT routes
Dropped kerbs - Various locations? | Rhuddlan | Dropped kerbs
Bryn Llys | Meliden | Resurfacing of section of existing PROW